## Sheet1
20190228 |  | NJ WebReads Migration
Task Status | Task ID | Task Name | Duration | Start | Finish | Predecessors
Completed | 1 | Kickoff Conference Call | 1 day | Thu 02/21/19 | Thu 02/21/19
Completed | 2 | Retrieve backup of CUL database | 1 day | Mon 02/25/19 | Mon 02/25/19
Completed | 3 | Stand up database in house | 1 day | Tue 02/26/19 | Tue 02/26/19 | 2
In Progress | 4 | Run distribution counts on key CUL tables | 3 days | Wed 02/27/19 | Fri 03/01/19 | 3
| 5 | Define any filters that need to be applied to purge old/unwanted data | 10 days | Mon 03/04/19 | Fri 03/15/19 | 4
| 6 | Map CUL data fields/values to WR equivalents. | 10 days | Mon 03/18/19 | Fri 03/29/19 | 5
| 7 | Define any data transformations required | 10 days | Mon 04/01/19 | Fri 04/12/19 | 6
| 8 | Perform data transformations to condition NJ database for WR UAT migration | 9 days | Mon 04/15/19 | Fri 04/26/19 | 7,5
| 9 | Perform test load of conditioned initial data extract into WR UAT, perform a PIMMS reconcile | 1 day | Fri 04/26/19 | Fri 04/26/19 | 8
UAT/Testing & Training Phase
| 10 | Retrieve backup of CUL database | 1 day | Mon 04/29/19 | Mon 04/29/19
| 11 | Perform data transformations to condition NJ database for WR UAT migration | 2 days | Tue 04/30/19 | Wed 05/01/19 | 10
| 12 | Perform test load of conditioned second data extract into WR UAT | 1 day | Thu 05/02/19 | Thu 05/02/19 | 11
| 13 | Quality Assurance testing on second data load into WR UAT, PIMMS reconcile | 2 day2 | Fri 05/03/19 | Mon 05/06/19 | 12
| 14 | User evaluation of second WR data load, staff training (Webex), testing DoD functionality/mailcards etc. | 24 days | Tue 05/07/19 | Thu 06 /06/19 | 13
| 15 | Plan for final migration extract. | 1 day | Tue 05/28/19 | Tue 05/28/19
Final Migration Phase
| 16 | NJ1A closed for day | 1 day | Fri 06/07/19 | Fri 06/07/19
| 17 | Conduct final extract, transformation and load (cutover) | 2 days | Fri 06/07/19 | Sat 06/08/19 | 15, 16
| 18 | Run PIMMS reconcile after migration and load. | 1 day | Sat 06/08/19 | Sat 06/08/19 | 17
| 19 | Make NJ instance of WR available in Production (live). | 1 day | Mon 06/10/19 | Mon 06/10/19 | 18
| 20 | User acceptance of Production WR installation | 1 day | Fri 06/14/19 | Fri 06/14/19 | 19